## Sheet1
Revised Schedule 8/14/17 7:31PM THREE WEEK SCHEDULE
Mt San Jacinto College San Jacinto Campus |  |  | DATES COVERED:
[5 empty] | Week 1 8/14 to 8/18 | [6 empty] | Week 2 8/21 to 8/25 | [6 empty] | Week 3 8/28 to 9/1
Site | AREA OR | ACTIVITY | Start Time | WEEK ONE | [6 empty] | WEEK TWO | [6 empty] | WEEK THREE
| Building(S) |  |  | MON. | TUE. | WED. | THUR. | FRI. | SAT. | SUN. | MON. | TUE. | WED. | THUR. | FRI. | SAT. | SUN. | MON. | TUE. | WED. | THUR. | FRI. | SAT. | SUN.
Menifee Campus | 500,250,260,300 | Pathway Survey All Rooms in buildings | 12:00 AM-8:00AM | x |  |  |  |  | OFF | OFF | [5 empty] | OFF | OFF | [5 empty] | OFF | OFF
Menifee Campus | 900 | pathway and cable install | 12:00 AM-8:00AM | x |  |  |  |  | OFF | OFF | [5 empty] | OFF | OFF | [5 empty] | OFF | OFF
Menifee Campus | 700,600 | Pathway Survey All Rooms in buildings | 12:00 AM-8:00AM |  | x |  |  |  | OFF | OFF | [5 empty] | OFF | OFF | [5 empty] | OFF | OFF
Menifee Campus | 900 | pathway and cable install | 12:00 AM-8:00AM |  | x |  |  |  | OFF | OFF | [5 empty] | OFF | OFF | [5 empty] | OFF | OFF
Menifee Campus | 2005,2004,2007,2006,400 | Pathway Survey All Rooms in buildings Access to MDF in building 400 | 12:00 AM-8:00AM |  |  | x |  |  | OFF | OFF | [5 empty] | OFF | OFF | [5 empty] | OFF | OFF
Menifee Campus | 900,800 | Horizontal Station side terminations building 900. Pathway and cable install building 800. Copper Testing and AP Install Building 900 | 12:00 AM-8:00AM |  |  | x |  |  | OFF | OFF | [5 empty] | OFF | OFF | [5 empty] | OFF | OFF
Menifee Campus | 400,1006,1007,1008,1009,,1010,1011,1012,1013 | Pathway Survey All Rooms in buildings | 12:00 AM-8:00AM |  |  |  | x |  | OFF | OFF | [5 empty] | OFF | OFF | [5 empty] | OFF | OFF
Menifee Campus | 800 | pathway and cable install | 12:00 AM-8:00AM |  |  |  | x |  | OFF | OFF | [5 empty] | OFF | OFF | [5 empty] | OFF | OFF
Menifee Campus | 1014,1015,1016,1017,1018,1019,1020,1021 | Pathway Survey All Rooms in buildings | 12:00 AM-8:00AM |  |  |  |  | x | OFF | OFF | [5 empty] | OFF | OFF | [5 empty] | OFF | OFF
Menifee Campus | 800 | pathway and cable install | 12:00 AM-8:00AM |  |  |  |  | x | OFF | OFF | [5 empty] | OFF | OFF | [5 empty] | OFF | OFF
Menifee Campus | 1022,5000,5001,5002,200,100 | Pathway Survey All Rooms in buildings. Access to MDF in building 200 | 12:00 AM-8:00AM | [5 empty] | OFF | OFF | X |  |  |  |  | OFF | OFF | [5 empty] | OFF | OFF
Menifee Campus | 800 | Horizontal station terminations.Copper Testing and AP Install Building 800 | 12:00 AM-8:00AM | [5 empty] | OFF | OFF | x |  |  |  |  | OFF | OFF | [5 empty] | OFF | OFF
Menifee Campus | 100 | Pathway Survey All Rooms in buildings | 12:00 AM-8:00AM | [5 empty] | OFF | OFF |  | x |  |  |  | OFF | OFF | [5 empty] | OFF | OFF
Menifee Campus | 500 | pathway and cable install | 12:00 AM-8:00AM | [5 empty] | OFF | OFF |  | x |  |  |  | OFF | OFF | [5 empty] | OFF | OFF
Menifee Campus | 500 | pathway and cable install/Horizontal station terminations.Copper Testing and AP Install Building 600 | 12:00 AM-8:00AM | [5 empty] | OFF | OFF |  |  | x |  |  | OFF | OFF | [5 empty] | OFF | OFF
Menifee Campus | 600 | pathway and cable install/Horizontal station terminations | 12:00 AM-8:00AM | [5 empty] | OFF | OFF |  |  |  | x |  | OFF | OFF | [5 empty] | OFF | OFF
Menifee Campus | 600,700 | Copper Testing and AP Install Building 600.pathway and cable install/Horizontal station terminations building 700 | 12:00 AM-8:00AM | [5 empty] | OFF | OFF |  |  |  |  | x | OFF | OFF | [5 empty] | OFF | OFF
Menifee Campus | 700 | pathway and cable install,Horizontal station terminations.Copper | 12:00 AM-8:00AM | [5 empty] | OFF | OFF | [5 empty] | OFF | OFF | x |  |  |  |  | OFF | OFF
Menifee Campus | 700,400 | Copper Testing and AP Install Building 600.pathway and cable install/Horizontal station terminations building 400 | 12:00 AM-8:00AM | [5 empty] | OFF | OFF | [5 empty] | OFF | OFF |  | x |  |  |  | OFF | OFF
Menifee Campus | 400 | pathway and cable install/Horizontal station terminations building 400 | 12:00 AM-8:00AM | [5 empty] | OFF | OFF | [5 empty] | OFF | OFF |  |  | x |  |  | OFF | OFF
Menifee Campus | 400,2005,2006,2007 | Copper Testing and AP Install Building 400.pathway and cable install/Horizontal station terminations building 2005,2006,2007 | 12:00 AM-8:00AM | [5 empty] | OFF | OFF | [5 empty] | OFF | OFF |  |  |  | x |  | OFF | OFF
Menifee Campus | 2005,2006,2007 | Copper Testing and AP Install Building 2005,2006,2007 | 12:00 AM-8:00AM | [5 empty] | OFF | OFF | [5 empty] | OFF | OFF |  |  |  |  | x | OFF | OFF
Comments: | Please note that this is a anticipated schedule and may change due to site conditions
Vector Foreman will cordinate times for access to IDF cabinets with assigned MSJC site contact on the scheduled day
Signed: | Peter Michel | [5 empty] | Date: | 2017-08-14
On Site Superintendent

## Sheet2
TWO WEEK SCHEDULE
SCHOOL: |  |  |  |  | DATES COVERED:
| AREA OR |  | WEEK ONE | [6 empty] | WEEK TWO
BLDG. | ROOM(S) | ACTIVITY | MON. | TUE. | WED. | THUR. | FRI. | SAT. | SUN. | MON. | TUE. | WED. | THUR. | FRI. | SAT. | SUN.
Comments:
Signed: Date:

## Sheet3
TWO WEEK SCHEDULE
SCHOOL: |  |  |  |  | DATES COVERED:
| AREA OR |  | WEEK ONE | [6 empty] | WEEK TWO
BLDG. | ROOM(S) | ACTIVITY | MON. | TUE. | WED. | THUR. | FRI. | SAT. | SUN. | MON. | TUE. | WED. | THUR. | FRI. | SAT. | SUN.
Comments:
Signed: Date: